## eco_trap_schedule
| Day | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
| Task | Overnights set up tent | Spray plants Count and add aphids | - | - | - | - | Count babies Move alates to unsprayed plant #2 Sample plant #1 | Count babies Move alates to unsprayed plant #2 Sample plant #1 | - | - | - | - | Count babies Move alates to unsprayed plant #3 Sample unsprayed plant #2 | Count babies Move alates to unsprayed plant #3 Sample unsprayed plant #2 | - | - | - | - | Count babies Sample unsprayed plant #3 | Count babies Sample unsprayed plant #3
| Wednesday Start | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday
| Tuesday Start | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Block #1 | Date | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22
| Status | complete | complete | complete | complete | complete | complete | complete | complete | complete | complete | complete | complete | complete | complete | complete | complete | incomplete | incomplete | incomplete | incomplete
Block #2 | Date | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12
| Status | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete
Block #3 | Date | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01
| Status | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete
Block #4 | Date | Thursday, June 12, 2025 | Friday, June 13, 2025 | Saturday, June 14, 2025 | Sunday, June 15, 2025 | Monday, June 16, 2025 | Tuesday, June 17, 2025 | Wednesday, June 18, 2025 | Thursday, June 19, 2025 | Friday, June 20, 2025 | Saturday, June 21, 2025 | Sunday, June 22, 2025 | Monday, June 23, 2025 | Tuesday, June 24, 2025 | Wednesday, June 25, 2025 | Thursday, June 26, 2025 | Friday, June 27, 2025 | Saturday, June 28, 2025 | Sunday, June 29, 2025 | Monday, June 30, 2025 | Tuesday, July 1, 2025
| Status | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete | incomplete

## weekly_ecotrap_tuesday_start
EcoTrap Fecundity Experiment #
Day | Task | Tuesday Start | Date
-1 | Overnights | Tuesday
0 | Spray plants Count and add aphids | Wednesday
1 | - | Thursday
2 | - | Friday
3 | - | Saturday
4 | - | Sunday
5 | - | Monday
6 | Count babies Move alates to unsprayed plant #2 Sample plant #1 | Tuesday
7 | - | Wednesday
8 | - | Thursday
9 | - | Friday
10 | - | Saturday
11 | - | Sunday
12 | Count babies Move alates to unsprayed plant #3 Sample unsprayed plant #2 | Monday
13 | - | Tuesday
14 | - | Wednesday
15 | - | Thursday
16 | - | Friday
17 | - | Saturday
18 | Count babies Sample unsprayed plant #3 | Sunday

## weekly_ecotrap_wednesday_start
EcoTrap Fecundity Experiment #
Day | Task | Wednesday Start | Date
-1 | Overnights | Wednesday
0 | Spray plants Count and add aphids | Thursday
1 | - | Friday
2 | - | Saturday
3 | - | Sunday
4 | - | Monday
5 | - | Tuesday
6 | Count babies Move alates to unsprayed plant #2 Sample plant #1 | Wednesday
7 | - | Thursday
8 | - | Friday
9 | - | Saturday
10 | - | Sunday
11 | - | Monday
12 | Count babies Move alates to unsprayed plant #3 Sample unsprayed plant #2 | Tuesday
13 | - | Wednesday
14 | - | Thursday
15 | - | Friday
16 | - | Saturday
17 | - | Sunday
18 | Count babies Sample unsprayed plant #3 | Monday

## weekly_ecotrap_thursday_start
EcoTrap Fecundity Experiment #
Day | Task | Thursday | Date
-1 | Overnights | Thursday
0 | Spray plants Count and add aphids | Friday
1 | - | Saturday
2 | - | Sunday
3 | - | Monday
4 | - | Tuesday
5 | - | Wednesday
6 | Count babies Move alates to unsprayed plant #2 Sample plant #1 | Thursday
7 | - | Friday
8 | - | Saturday
9 | - | Sunday
10 | - | Monday
11 | - | Tuesday
12 | Count babies Move alates to unsprayed plant #3 Sample unsprayed plant #2 | Wednesday
13 | - | Thursday
14 | - | Friday
15 | - | Saturday
16 | - | Sunday
17 | - | Monday
18 | Count babies Sample unsprayed plant #3 | Tuesday